## Feuille1
Planning and Recipe
(one document per team)
The aim of this doc is to define as precisely as possible the tasks and the "what to do" planning. Fill all the red sections.
Project Title | InMoov Robot Interactif
Project Number | my number
Team Referent | Corentin Lemaitre
Other Team Members | Rayan Galetta, Rabah Houaoui, Kristof Szucs
Team Mentor | Zeinab MHANNA ; zeinab.mhanna@gmail.com
Project Partner | Company |  | First and last name for company contact |  | E-mail
Planning | [6 empty] | Risks Management |  | Skills |  | Recipe
Tasks | Starting Date | Duration | Deadline | Responsable | Who realise | Ressources | Risks | Action if necessary | Used | Acquired | Validation criteria | Success | If not : justification and solution
State Of Art | 2017-09-21 | 43 days | 2017-11-03 | Cor | all | Press, Web, InMoov | Incompatibility with other 2 projects of InMoov |  | Searches Comprehension Communication |  | identify the subject
InMoov community research | 2017-09-21 |  | 2017-11-10 | Rab | all | InMoov community | take the best from the community while aiming to go beyond | Contact other InMoov users, to better understand the project in it's globality
World Wide robots tech | 2017-09-23 |  | 2017-11-10 | K | all | Web, Press
First planning | 2017-09-21 | 22 | 2017-10-13 | Ray | all | Excel,Gantt | not precise enough | Ajust it day by day | Short-medium-long term previsions |  | No big modifications
Coding | 2017-10-18 | 131 | 2018-02-26 | Ray | all | Websites, existing project, teachers
Searches on MyRobotLab | 2017-10-18 | 16 | 2017-11-03 | Cor | all | Websites, existing project, teachers | Check for compability with osers tool |  | seaches + doc reading |  | Install MyRobotLab
Searches existing software | 2017-10-25 | 14 | 2017-11-08 | Ray | all | Websites, existing project, teachers | No real risks: the robot's code will also be used by DVB |  | searches + code comprehension |  | Can read the code entirely
Speech recognition | 2017-11-09 | 48 | 2017-12-27 | Ray | all | Websites, existing project, teachers | Not compatible with hardware, no control over data | Change hardware(or software) , change the process to keep track of the data | hardware knowledge ¦¦ Api and database skills |  | Best process of analysing sounds and low rates of speech recognitions errors
Text to speech software | 2017-11-20 | 59 | 2018-01-18 | Ray | all | Websites, existing project, teachers | jerky speech, intonation issues, robot like speech | relate on new tech not commonly used but promising in results |  |  | Close to human speech, with fluid talk and natural speech behavior
Code an Artificial Intelligence -- Chat Bot | 2017-12-28 | 60 | 2018-02-26 | Ray/Cor | all | Websites, existing project, teachers | Can't modify the code to implement specific behavior to the robot | Use a less powerfull chatbot and implement specific task to lower the flexibility but better the respons to know scenario |  |  | AI capable of maintening small talks, recognise discussion partern and better itself with machine learning process
Verify the compatibility of the code | 2017-12-28 | 60 | 2018-02-26 | all | all | Websites, existing project, teachers | Our code isn't compatible with the other group's | make the codes usable for all. Each group must have access to the others groupe code | Communication, programming (python, arduino, Java…) |  | The 3 groups code work perfectlly together
Create a database | 2017-11-10 |  | 2018-02-26 | X | all | Websites, existing project, teachers | Database not well managed to store primary needed data, and future needed data | Update the database, and think of possible data needed by all users on InMoov |  |  | The database is capable of transmiting key data to the AI to implement its speech but also able to store data collecting while speeking to the robot.
Database management | 2017-11-10 |  | 2018-02-26 | X | all | Websites, existing project, teachers | wrong type of data stored, or incorectly stored | Reset the data collecting process, and analyse the scenario where they are collected |  |  | maintening a "clean" database, with needed data and easy access to them.
Robot modeling/construction | 2017-10-30 | 67 | 2018-01-05 | Kris | all | Catia/Solidworks
Face modeling | 2017-10-30 | 18 | 2017-11-17 | X | all | Catia/Solidworks | No face model achieved | Will only add components on the default head | Modeling |  | Modified InMoov head added on the rest of the robot + no component collisions
Jaw montage | 2017-11-27 | 25 | 2017-12-22 | X | all | Catia/Solidworks | Jaw has not been modified | Jaw movement acording of the speech | Modeling |  | modified jaw working
Face energy source | 2017-12-01 | 35 | 2018-01-05 | X | all | Catia/Solidworks | Our face is not powered properly | Emergency battery |  |  | all the face parts are well functionning
Mecanical Reactions | 2018-01-08 | 46 | 2018-02-23 | Cor | all | Python/Arduino/Java
Link between speech sound and mecanical parts | 2018-01-08 | 46 | 2018-02-23 | X | all | Python/Arduino/Java | Jaw movement not sync with speech | re-set the synchronisation between speech and movement |  |  | Mouth movement sync with the flow of the speech // range of the movement related to the volume of the sound produced
Link between containt of speech and global mechanial movement | 2018-01-08 | 46 | 2018-02-23 | X | all | Python/Arduino/Java | global gesture that dont fit the sense of the speech | create a proper link between the emotion team and our, to create more adequate movements |  |  | Synchronized general movement with emotion and context
PRM & deadlines | 2017-10-31 | 149 | 2018-03-29 | Rab | All | Soft Skills | X | X
PRM Review 1 | 2017-10-31 | 0 | 2017-10-31 | X | All | Soft Skills | X | X
Pitchs | 2017-11-07 | 0 | 2017-11-07 | X | All | Soft Skills | X | X
PRM Review 2 | 2017-11-21 | 0 | 2017-11-21 | X | All | Soft Skills | X | X
PRM Review 3 | 2017-12-05 | 0 | 2017-12-05 | X | All | Soft Skills | X | X
Project Review 1 | 2017-12-12 | 0 | 2017-12-12 | X | All | Soft Skills | X | X
PRM Review 4 | 2018-01-16 | 0 | 2018-01-16 | X | All | Soft Skills | X | X
PRM Review 5 | 2018-01-30 | 0 | 2018-01-30 | X | All | Soft Skills | X | X
Project Review 2 | 2018-02-12 | 0 | 2018-02-12 | X | All | Soft Skills | X | X
PRM Review 6 | 2018-03-13 | 0 | 2018-03-13 | X | All | Soft Skills | X | X
Show Room & closure | 2018-03-29 | 0 | 2018-03-29 | X | All | Soft Skills | X | X