## Feuille1
Planning and Recipe
(one document per team)
The aim of this doc is to define as precisely as possible the tasks and the "what to do" planning. Fill all the red sections.
Project Title | Robot Cognitif
Project Number | 65
Team Referent | MARTIN Jérémy
Other Team Members | EKHTERAEI Aria, GUILLAUME Thomas, MEZOUAR Chloé
Team Mentor | Jean-Philippe Lelievre
Project Partner | DaVinciBot |  | LEMAITRE Corentin et PARILUSYAN Brice |  | corentin.lemaitre@devinci.fr
Planning | [6 empty] | Risks Management |  | Skills |  | Recipe
Tasks | Starting Date | Duration | Deadline | Responsable | Who realise | Ressources | Risks | Action if necessary | Used | Acquired | Validation criteria | Success | If not : justification and solution
1-General Facial Detection | 2017-10-10 | 21 days | 2017-10-31 | Martin Jérémy | All | Fablab
1-1-Face recognition ( not facial features) | 2017-10-10 | 30 days | 2017-11-09 | Martin Jérémy | All | Fablab | Incompatible camera | buy a new camera | coding
1-2-Head tracking robot | 2017-10-20 | 20 days | 2017-11-09 | Martin Jérémy | All | Fablab | rigid motorisation | change motors | coding
2-Targeted facial detection | 2017-11-01 | 61 days | 2017-12-31 | Martin Jérémy | All | Fablab |  |  | coding
2-1-Facial features recognition | 2017-11-01 | 21 days | 2017-11-15 | Martin Jérémy | All | Fablab |  |  | coding
2-2-Make and test a database with information | 2017-11-15 | 15 days | 2017-11-30 | Martin Jérémy | All | Fablab |  |  | coding
2-3-Develop a simple record series | 2017-12-01 | 15 days | 2017-12-15 | Martin Jérémy | All | Fablab |  |  | coding
2-4-Linking and applying the various points above | 2017-12-15 | 10 days | 2017-12-31 | Martin Jérémy | All | Fablab |  |  | coding